## Slide 1: PM REVIEW
PONG PONG
Team 4
AMOS TAN | JENNIFER YAP|KOH CHU QIAN | REMY NG | TANG SHING HEI

## Slide 2
  Project Overview
  Iterations
  Iteration 1 Review
  Roles and Responsibilities
  Iteration 2
Content Page

## Slide 3: Project Overview

## Slide 4: Functionalities
Black band
No intention to drop any functionalities as of yet
Currently using Spring Framework + Hibernate
MVC
Feature-boxing

## Slide 5: Overall Schedule
14 days | 8 days | 11 days | 10 days | 5 days | Buffer | 7 days
66 hours | 66 hours | 48 hours | 44 hours | 31 hours | 5 days | 57 hours
START
END
Iteration 1
Iteration 2
Iteration 3
Iteration 4
Iteration 5
Iteration 6
WEEK
5
7
8
10
11
12
13

## Slide 6: Overall Schedule
Iteration | Start | End | Total Days
Iteration 1 (Week 5 – Week 7) | 17 September | 27 September | 11 days
 | 17 September | 30 September | 14 days
Iteration 2 (Week 7 – Week 8) | 1 October | 8 October | 8 days
Iteration 3 (Week 8 – Week 10) | 9 October | 19 October | 11 days
Iteration 4 (Week 10 – Week 11) | 20 October | 29 October | 10 days
Iteration 5 (Week 11 – Week 12) | 30 October | 3 November | 5 days
Buffer (Week 12) | 4 November | 8 November | 5 days
Iteration 6 (Week 13) | 9 November | 15 November | 7 days

## Slide 7: Milestones
PM Review
Supervisor
Meeting 1
Supervisor
Meeting 2
Supervisor
Meeting 3
User Acceptance Test
Final Presentation
WEEK
5
7
8
10
11
13
Chu Qian
Remy
Jennifer
Shing Hei
Amos
Remy
15

## Slide 8: Planned Iterations
 | Tasks
Iteration 1 | Bootstrap and Login Functionality
Iteration 2 | Basic App Reports, Top-K and Smartphone Overuse Report
Iteration 3 | Loading/Deleting Location data, Heatmap, Social Activeness Report
Iteration 4 | Graphical UIs and Advanced Smartphone Overuse Report
Iteration 5 | Optimisation of functionalities
Iteration 6 | Improvements of functions after UAT

## Slide 9: Iteration Overview

## Slide 10: Iteration 1
Research
Test Deployment Case
Bootstrap
Integration, Testing, Documentation, Deployment
Supervisor Meeting Review
Review of iteration
Login
Diagrams
1 Day
2 Days
1 Day
1 Day
2 Days
Bootstrap
1 Day
5 Days
2 Days
Pair 1: Amos & Shing Hei
Pair 2: Remy & Jennifer
START
END
Critical Path:
11 Days

## Slide 11
Iteration 2
Research
Test Deployment Case
Basic App Usage Report
PM Review
Top-K App Usage Report
UI Design & Diagrams
1 Day
1 Day
3 Days
SmartPhone Overuse Report
2 Days
2 Days
1 Day
Pair 1: Jennifer & Shing Hei
Pair 2: Amos & Chu Qian
START
Review of iteration
Integration, Testing, Documentation, Deployment
END
Critical Path:
Top-K App Usage & Smartphone
1 Day
consists of
Basic App Report
1 Day
consists of
8 Days

## Slide 12
Iteration 3
Research
Test Deployment Case
Smartphone Usage Heat-map
Supervisor Meeting Review
Loading Location Data
UI Design & Diagrams
1 Day
4 Days
Deletion of Location Data
2 Days
4 Days
1 Day
1 Day
Pair 1: Chu Qian & Remy
Pair 2: Amos & Shing Hei
START
Review of iteration
Social Activeness
3 Days
Integration, Testing, Documentation, Deployment
END
Critical Path:
2 Days
11 Days

## Slide 13
Iteration 4
Research
Test Deployment Case
Advanced Smartphone Overuse Report
Supervisor Meeting
Graphical UIs (HeatMap & Chart)
UI Design & Diagrams
1 Day
6 Days
5 Days
2 Days
Pair 1: Amos & Remy
Pair 2: Chu Qian & Jennifer
START
Review of iteration
Integration, Testing, Documentation, Deployment
END
Critical Path:
2 Days
10 Days

## Slide 14
Iteration 5
Research & Diagram
Test Deployment Case
Optimise Basic App Usage, Heatmap
Optimise Bootstrap, Top K
1 Day
1 Day
2 Days
3 Days
2 Days
1 Day
Pair 1: Jennifer & Chu Qian
Pair 2: Remy & Shing Hei
START
Review of iteration
Integration, Testing, Documentation, Deployment
END
Optimise Smartphone, Social Activeness
Critical Path:
2 Days
10 Days

## Slide 15
Iteration 6
Research & Diagram
Test Deployment Case
UAT Changes: Top K, Basic App Usage, Smartphone
UAT Changes: Bootstrap, HeatMap, Social Activeness
3 Days
2 Days
1 Day
Pair 1: Jennifer & Amos
Pair 2: Chu Qian & Shing Hei
START
Review of iteration
END
UAT Review
1 Day
Bootstrap, HeatMap, Social Activeness
1 Day
Top K, Basic App Usage, Smartphone
1 Day
consists of
consists of
Critical Path:
Integration, testing, documentation, Deployment
1 Day
6 Days

## Slide 16: Iteration 1 Review

## Slide 17: Schedule Metrics
Iteration | Planned | Actual | Schedule Metrics
1 | 11 Days | 14 Days | 0.79

## Slide 18: Bug Metrics
S/N | Issue Date | Status | Functionality | Description | Severity | Mitigation
1 | 27/9/2015 | Fixed | Login | Failed to redirect user back to login for ../bootstrap | 5 | Resolve Immediately
2 | 27/9/2015 | Fixed | Bootstrap | Success message not shown when uploading CSV files | 5 | Resolve Immediately
3 | 28/9/2015 | Fixed | Bootstrap | Error messages are displayed together with an additional string of output | 1 | Resolve Immediately

## Slide 19: Bug Metrics
S/N | Issue Date | Status | Functionality | Description | Severity | Mitigation
4 | 28/9/2015 | Fixed | Bootstrap | JSON Bootstrap function does not carry out common validations | 5 | Resolve Immediately
5 | 28/9/2015 | Fixed | Bootstrap | Incorrect line number output to bootstrap UI for duplicate rows | 5 | Resolve Immediately
6 | 29/9/2015 | Ignored | Login | JSON field is incorrectly named | 1 | Resolve in Iteration 2
7 | 29/9/2015 | Ignored | Bootstrap | Common validation for Bootstrap error message is incorrectly named | 1 | Resolve in iteration 2

## Slide 20: Iteration 1 Metrics
Planned Iteration Dates: 17/09/2015 – 27/9/2015
Actual Iteration Dates: 17/09/2015 – 30/9/2015
Delay was due to debugging for bootstrap
Schedule Metrics at 0.79
  Use buffer days. 5 buffer days left.
  No functionalities to be dropped
Current Bug Metrics Value = 2

## Slide 21: Learning Points
Keep track of wiki closely
Track test cases closely
Check and double check before deployment

## Slide 22: Iteration 2
Project Manager: Remy
Pair Programmers:
  Shing Hei & Jennifer
  Amos & Chu Qian
Planning phase is done

## Slide 23: Roles and Responsibilities

## Slide 24: Project Manager
Schedule tasks and PP Sessions
Arrange for meetings
Ensure deadlines are met
Plan test cases

## Slide 25: Coder
Research
Teach
Code sharing
Finish up assigned functionalities

## Slide 26: Role Rotation
 | PM | Pair 1 | Pair 2
Iteration 1 | Chu Qian | Remy & Jennifer | Amos & Shing Hei
Iteration 2 | Remy | Amos & Chu Qian | Jennifer & Shing Hei
Iteration 3 | Jennifer | Remy & Chu Qian | Amos & Shing Hei
Iteration 4 | Shing Hei | Amos & Remy | Chu Qian & Jennifer
Iteration 5 | Amos | Remy & Shing Hei | Jennifer & Chu Qian
Iteration 6 | Remy | Amos & Jennifer | Shing Hei & Chu Qian

## Slide 27
Q & A

## Slide 28
THANK YOU