## Slide 1: Supervisor Meeting 2
PONG PONG
Team 4
AMOS TAN | JENNIFER YAP|KOH CHU QIAN | REMY NG | TANG SHING HEI

## Slide 2
  Overall Schedule
  Iterations
  Milestones
  Iteration 2 Review
  Iteration 3
Content Page

## Slide 3: Overall Schedule
14 days |  | 9 days |  | 11 days |  | 10 days |  | 5 days |  | Buffer | 14 days | 
66 hours |  | 86 hours |  | 73 hours |  | 52 hours |  | 36 hours |  | 5 days | 57 hours | 
P | NP | P | NP | P | NP | P | NP | P | NP |  | P | NP
46.5 | 19.5 | 74 | 12 | 55 | 18 | 40 | 12 | 29 | 7 |  | 38 | 29
START
END
Iteration 1
Iteration 2
Iteration 3
Iteration 4
Iteration 5
Iteration 6
WEEK
5
7
8
10
11
12
14
Legend:
P  Programming
NP  Non-programming

## Slide 4: Overall Schedule
Iteration | Start | End | Total Days
Iteration 1 (Week 5 – Week 7) | 17 September | 27 September | 11 days
 | 17 September | 30 September | 14 days
Iteration 2 (Week 7 – Week 8) | 1 October | 8 October | 8 days
 | 1 October | 9 October | 9 days
Iteration 3 (Week 8 – Week 10) | 9 October | 19 October | 11 days
Iteration 4 (Week 10 – Week 11) | 20 October | 29 October | 10 days
Iteration 5 (Week 11 – Week 12) | 30 October | 3 November | 5 days
Buffer (Week 12) | 4 November | 8 November | 5 days
Iteration 6 (Week 14) | 9 November | 22 November | 14 days

## Slide 5: Milestones
PM Review
Supervisor
Meeting 1
Supervisor
Meeting 2
Supervisor
Meeting 3
User Acceptance Test
Final Presentation
WEEK
5
7
8
10
11
13
Chu Qian
Remy
Jennifer
Shing Hei
Amos
Remy
14

## Slide 6: Planned Iterations
 | Tasks
Iteration 1 | Bootstrap and Login Functionality
Iteration 2 | Basic App Reports, Top-K and Smartphone Overuse Report
Iteration 3 | Loading/Deleting Location data, Heatmap, Social Activeness Report
Iteration 4 | Graphical UIs and Advanced Smartphone Overuse Report
Iteration 5 | Optimisation of functionalities
Iteration 6 | Improvements of functions after UAT

## Slide 7: Role Rotation
 | PM | Pair 1 | Pair 2
Iteration 1 | Chu Qian | Remy & Jennifer | Amos & Shing Hei
Iteration 2 | Remy | Amos & Chu Qian | Jennifer & Shing Hei
Iteration 3 | Jennifer | Remy & Chu Qian | Amos & Shing Hei
Iteration 4 | Shing Hei | Amos & Remy | Chu Qian & Jennifer
Iteration 5 | Amos | Remy & Shing Hei | Jennifer & Chu Qian
Iteration 6 | Remy | Amos & Jennifer | Shing Hei & Chu Qian

## Slide 8: Iteration Overview

## Slide 9: Iteration 1
Research
Test Deployment Case
Bootstrap
Integration, Testing, Documentation, Deployment
Supervisor Meeting Review
Review of iteration
Login
Diagrams
1 Day
2 Days
1 Day
1 Day
2 Days
Bootstrap
1 Day
5 Days
2 Days
Pair 1: Amos & Shing Hei
Pair 2: Remy & Jennifer
START
END
Critical Path:
11 Days

## Slide 10
Iteration 2
Research
Test Deployment Case
Basic App Usage Report
PM Review
Top-K App Usage Report
UI Design & Diagrams
1 Day
1 Day
3 Days
SmartPhone Overuse Report
2 Days
2 Days
1 Day
Pair 1: Jennifer & Shing Hei
Pair 2: Amos & Chu Qian
START
Review of iteration
Integration, Testing, Documentation, Deployment, Regression Testing
END
Critical Path:
Top-K App Usage & Smartphone
1 Day
consists of
Basic App Report
1 Day
consists of
8 Days

## Slide 11
Iteration 3
Research
Test Deployment Case
Smartphone Usage Heat-map
Loading Location Data
UI Design & Diagrams
1 Day
3 Days
Deletion of Location Data
1 Day
3 Days
1 Day
Pair 1: Chu Qian & Remy
Pair 2: Amos & Shing Hei
START
Review of iteration
Social Activeness
2 Days
Integration, Testing, Documentation, Deployment, Regression Testing
END
Critical Path:
2 Days
11 Days
3 Days
Supervisor Meeting Review

## Slide 12
Iteration 4
Research
Test Deployment Case
Advanced Smartphone Overuse Report
Supervisor Meeting
Graphical UIs (HeatMap & Chart)
UI Design & Diagrams
1 Day
6 Days
5 Days
2 Days
Pair 1: Amos & Remy
Pair 2: Chu Qian & Jennifer
START
Review of iteration
Integration, Testing, Documentation, Deployment, Regression Testing
END
Critical Path:
2 Days
10 Days

## Slide 13
Iteration 5
Research & Diagram
Test Deployment Case
Optimise Basic App Usage, Heatmap
Optimise Bootstrap, Top K
1 Day
1 Day
2 Days
3 Days
2 Days
1 Day
Pair 1: Jennifer & Chu Qian
Pair 2: Remy & Shing Hei
START
Review of iteration
Integration, Testing, Documentation, Deployment, Regression Testing
END
Optimise Smartphone, Social Activeness
Critical Path:
2 Days
10 Days

## Slide 14
Iteration 6
Research & Diagram
Test Deployment Case
UAT Changes: Top K, Basic App Usage, Smartphone
UAT Changes: Bootstrap, HeatMap, Social Activeness
3 Days
2 Days
1 Day
Pair 1: Jennifer & Amos
Pair 2: Chu Qian & Shing Hei
START
Review of iteration
END
UAT Review
1 Day
Bootstrap, HeatMap, Social Activeness
1 Day
Top K, Basic App Usage, Smartphone
1 Day
consists of
consists of
Critical Path:
Integration, testing, documentation, Deployment, Regression Testing
1 Day
6 Days

## Slide 15: Iteration 2 Review

## Slide 16: Schedule Metrics
Iteration | Planned | Actual | Schedule Metrics
1 | 11 Days | 14 Days | 0.79
2 | 8 Days | 9 Days | 0.88

## Slide 17: Iteration 2 Metrics
Planned Iteration Dates: 01/10/2015 – 08/10/2015
Actual Iteration Dates: 01/10/2015 – 09/10/2015
Delay was due to the overrun of most pair programming sessions
Schedule Metrics at 0.88
  Iteration 3 started on the same day Iteration 2 ended  buffer days unaffected (5 days)
  No functionalities to be dropped
Current Bug Metrics Value = 1

## Slide 18: Learning Points
Allocate more hours to planning
Don’t schedule short PP sessions (1 hour)  unproductive

## Slide 19: Iteration 3
Project Manager: Jennifer
Pair Programmers:
  Shing Hei & Amos
  Remy & Chu Qian
Planning phase is done
Pair programming sessions started for
  Loading of location data
  Smartphone usage heat map

## Slide 20
Q & A

## Slide 21
THANK YOU