## Iteration 1
Type of Tasks | Start Date | End Date | Hours Needed | Assigned To
ITERATION 1 - PM: Chu Qian | 2015-09-18 | 2015-09-27 | 58 | Chu Qian
Non-Coding |  |  | 19
Research | 2015-09-18 | 2015-09-27 | 2 | Chu Qian
Use Case Diagram, Domain Diagram, Use Case Scenario | 2015-09-18 | 2015-09-18 | 2 | Chu Qian
System Sequence Diagram, Sequence Diagram | 2015-09-18 | 2015-09-20 | 5 | Chu Qian
Class Diagram | 2015-09-19 | 2015-09-20 | 1 | Chu Qian
ER Diagram, Logical Diagram | 2015-09-19 | 2015-09-20 | 3 | Chu Qian
Test Deployment Cases | 2015-09-21 | 2015-09-21 | 2 | Chu Qian
Supervisor Meeting Review | 2015-09-22 | 2015-09-22 | 1 | Chu Qian
Review of Iteration | 2015-09-27 | 2015-09-27 | 1 | Chu Qian
Review of Code | 2015-09-27 | 2015-09-27 | 2 | Chu Qian
Coding |  |  | 39
Login + JSON | 2015-09-23 | 2015-09-26 | 8 | Amos, Shing Hei
[Backend] Entity classes (DAO) + Controller | 2015-09-23 | 2015-09-26 | 6 | Amos, Shing Hei
[Frontend] View | 2015-09-23 | 2015-09-26 | 2 | Amos, Shing Hei
Bootstrap + JSON | 2015-09-22 | 2015-09-26 | 26 | Remy, Jennifer
Upload zip files | 2015-09-22 | 2015-09-26 | 3 | Remy, Jennifer
Read data | 2015-09-22 | 2015-09-26 | 2 | Remy, Jennifer
Validate data | 2015-09-22 | 2015-09-26 | 7 | Remy, Jennifer
Store data into SQL | 2015-09-22 | 2015-09-26 | 8 | Remy, Jennifer
[Backend] Entity classes, DAO | 2015-09-22 | 2015-09-26 | 3 | Remy, Jennifer
[Frontend] View | 2015-09-22 | 2015-09-26 | 3 | Amos, Shing Hei
Integration, testing/debug, Documentation, Deployment | 2015-09-26 | 2015-09-27 | 5 | Amos, Shing Hei, Remy, Jennifer
Login | 2015-09-26 | 2015-09-27 | 2 | Amos, Shing Hei
Bootstrap | 2015-09-26 | 2015-09-27 | 3 | Remy, Jennifer

## Iteration 2
Type of Tasks | Start Date | End Date | Hours Needed | Assigned To
ITERATION 2 - PM: Remy | 2015-09-28 | 2015-10-06 | 50 | Remy
Non-Coding |  |  | x
Research | 2015-09-28 | 2015-09-30 | 2 | Remy
Design (UI), Wire Framing | 2015-09-28 | 2015-09-30 | 1 | Remy
Review Diagrams | 2015-09-28 | 2015-09-30 | 4 | Remy
PM Review | 2015-10-02 | 2015-10-02 | 2 | Remy
Test Deployment Cases | 2015-09-28 | 2015-09-30 | 2 | Remy
Code Review | 2015-10-06 | 2015-10-06 | 2 | Remy
Review Of Iteration | 2015-10-06 | 2015-10-06 | 1 | Remy
Coding
Basic App Usage Report + JSON |  |  | 13 | Amos, Chu Qian
DAO & Controller | 2015-09-30 | 2015-10-05 | 7 | Amos, Chu Qian
Breakdown by usage time category (e.g., High/Medium/Low) UI | 2015-09-30 | 2015-10-05 | 1.5 | Amos, Chu Qian
Breakdown by usage time category and demographics UI | 2015-09-30 | 2015-10-05 | 1.5 | Amos, Chu Qian
Breakdown by app category UI | 2015-09-30 | 2015-10-05 | 1.5 | Amos, Chu Qian
Diurnal pattern of app usage time UI | 2015-09-30 | 2015-10-05 | 1.5 | Amos, Chu Qian
Top-K app Usage Report (For the INDIVDUAL user) + JSON | 2015-09-30 | 2015-10-05 | 7 | Shing Hei, Jennifer
DAO & Controller | 2015-09-30 | 2015-10-05 | 4 | Shing Hei, Jennifer
Top-k most used apps (given a school) UI | 2015-09-30 | 2015-10-05 | 1 | Shing Hei, Jennifer
Top-k students with most app usage (given an app category) UI | 2015-09-30 | 2015-10-05 | 1 | Shing Hei, Jennifer
Top-k schools with most app usage (given an app category) UI | 2015-09-30 | 2015-10-05 | 1 | Shing Hei, Jennifer
Smartphone Overuse Report + JSON | 2015-09-30 | 2015-10-05 | 6 | Shing Hei, Jennifer
DAO & Controller | 2015-09-30 | 2015-10-05 | 5 | Shing Hei, Jennifer
Smartphone Overuse Report UI | 2015-09-30 | 2015-10-05 | 1 | Shing Hei, Jennifer
Integration, testing/debug, Documentation, Deployment | 2015-10-05 | 2015-10-06 | 10 | Amos, Chu Qian, Shing Hei, Jennifer
Basic App Usage Report | 2015-10-05 | 2015-10-06 | 4 | Amos, Chu Qian
Top-k app Usage Report | 2015-10-05 | 2015-10-06 | 3 | Shing Hei, Jennifer
Smartphone Overuse Report | 2015-10-05 | 2015-10-06 | 3 | Shing Hei, Jennifer

## Iteration 3
Type of Tasks | Start Date | End Date | Hours Needed | Assigned To
ITERATION 3 - PM: Jennifer | 2015-10-07 | 2015-10-15 | 48 | Jennifer
Non-Coding |  |  | 11 | Jennifer
Research | 2015-10-07 | 2015-10-08 | 2 | Jennifer
Review of Diagram | 2015-10-07 | 2015-10-07 | 2 | Jennifer
UI Planning | 2015-10-08 | 2015-10-08 | 1 | Jennifer
Test Development Cases | 2015-10-07 | 2015-10-08 | 2 | Jennifer
Supervisor Meeting | 2015-10-13 | 2015-10-13 | 1 | Jennifer
Review Of Iteration | 2015-10-15 | 2015-10-15 | 1 | Jennifer
Code Review | 2015-10-15 | 2015-10-15 | 2 | Jennifer
Coding
Location Data + JSON | 2015-10-08 | 2015-10-14 | 15 | Remy, Chu Qian
Loading Location Data - Bootstrapping with location data | 2015-10-08 | 2015-10-14 | 10 | Remy, Chu Qian
Deletion of Location Data | 2015-10-08 | 2015-10-14 | 5 | Remy, Chu Qian
Smartphone Usage Heatmap + JSON | 2015-10-08 | 2015-10-14 | 5 | Shing Hei, Amos
DAO & Controller | 2015-10-08 | 2015-10-14 | 4 | Shing Hei, Amos
Smartphone Usage Heatmap UI | 2015-10-08 | 2015-10-14 | 1 | Shing Hei, Amos
Social Activeness + JSON | 2015-10-08 | 2015-10-14 | 5 | Shing Hei, Amos
DAO & Controller | 2015-10-08 | 2015-10-14 | 4 | Shing Hei, Amos
Social Activeness UI | 2015-10-08 | 2015-10-14 | 1 | Shing Hei, Amos
Integration, testing/debug, Documentation, Deployment | 2015-10-14 | 2015-10-15 | 12 | Remy, Chu Qian, Shing Hei, Amos
Loading Location Data, Bootstrapping with location data | 2015-10-14 | 2015-10-15 | 4 | Remy, Chu Qian
Deletion Of Location Data | 2015-10-14 | 2015-10-15 | 3 | Remy, Chu Qian
Usage Heatmap | 2015-10-14 | 2015-10-15 | 3 | Amos, Shing Hei
Social Activeness | 2015-10-14 | 2015-10-15 | 2 | Amos, Shing Hei

## Iteration 4
Type of Tasks | Start Date | End Date | Hours Needed | Assigned To
ITERATION 4 - PM: Shing Hei | 2015-10-16 | 2015-10-27 | 44 | Shing Hei
Non-Coding |  |  | 12 | Shing Hei
Research | 2015-10-16 | 2015-10-16 | 2 | Shing Hei
Review of Diagram | 2015-10-16 | 2015-10-17 | 2 | Shing Hei
UI Planning | 2015-10-16 | 2015-10-16 | 1 | Shing Hei
Test Development | 2015-10-16 | 2015-10-18 | 2 | Shing Hei
Supervisor Meeting | 2015-10-27 | 2015-10-27 | 2 | Shing Hei
Review Of Iteration | 2015-10-27 | 2015-10-27 | 1 | Shing Hei
Code Review | 2015-10-27 | 2015-10-27 | 2 | Shing Hei
Coding
Advanced Smartphone Overuse Report + JSON | 2015-10-18 | 2015-10-25 | 9 | Jennifer, Chu Qian
DAO & Controller | 2015-10-18 | 2015-10-25 | 7 | Jennifer, Chu Qian
Advanced Smartphone Overuse Report UI | 2015-10-18 | 2015-10-25 | 2 | Jennifer, Chu Qian
Graphical UIs (Heatmap and Chart) + JSON | 2015-10-18 | 2015-10-25 | 12 | Amos, Remy
DAO & Controller | 2015-10-18 | 2015-10-25 | 4 | Amos, Remy
Graphical UIs (Heatmap and Chart) UI | 2015-10-18 | 2015-10-25 | 8 | Amos, Remy
Integration, testing/debug, Documentation, Deployment | 2015-10-25 | 2015-10-27 | 11 | Amos, Remy, Jennifer, Chu Qian
Advanced smartphone overuse | 2015-10-25 | 2015-10-27 | 5 | Jennifer, Chu Qian
Graphical UI | 2015-10-25 | 2015-10-27 | 6 | Amos, Remy

## Iteration 5
Type of Tasks | Start Date | End Date | Hours Needed | Assigned To
ITERATION 5 - PM: Amos | 2015-10-28 | 2015-11-03 | 31 | Amos
Non-Coding |  |  | 7 | Amos
Research | 2015-10-28 | 2015-10-28 | 1 | Amos
Review of Diagram | 2015-10-28 | 2015-10-28 | 1 | Amos
Test Development cases | 2015-10-28 | 2015-10-28 | 2 | Amos
Code Review | 2015-11-03 | 2015-11-03 | 2 | Amos
Review Of Iteration | 2015-11-03 | 2015-11-03 | 1 | Amos
Coding
Fast Queries for: |  |  | 14 | Chu Qian, Jennifer, Remy, Shing Hei
Bootstrap | 2015-10-28 | 2015-11-02 | 3 | Chu Qian, Jennifer
Top K | 2015-10-28 | 2015-11-02 | 2 | Chu Qian, Jennifer
Basic App Usage | 2015-10-28 | 2015-11-02 | 2 | Remy, Shing Hei
Heat Map | 2015-10-28 | 2015-11-02 | 2 | Remy, Shing Hei
Smart phone Overuse & Advanced | 2015-10-28 | 2015-11-02 | 3 | Remy, Shing Hei
Social Activeness | 2015-10-28 | 2015-11-02 | 2 | Remy, Shing Hei
Integration, testing/debug, Documentation, Deployment | 2015-11-02 | 2015-11-03 | 10 | Chu Qian, Jennifer, Remy, Shing Hei
Bootstrap | 2015-11-02 | 2015-11-03 | 2 | Jennifer, Chu Qian
Top K | 2015-11-02 | 2015-11-03 | 2 | Jennifer, Chu Qian
Basic App Usage & Heat Map | 2015-11-02 | 2015-11-03 | 3 | Shing Hei, Remy
Smart phone Overuse & Advanced& Social Activeness | 2015-11-02 | 2015-11-03 | 3 | Shing Hei, Remy

## Iteration 6
Type of Tasks | Start Date | End Date | Hours Needed | Assigned To
ITERATION 6 - PM: Remy | 2015-11-05 | 2015-11-20 | 57 | Remy
Non-Coding |  |  | 29
Planning | 2015-11-05 | 2015-11-05 | 2 | Remy
Diagram Review | 2015-11-05 | 2015-11-05 | 2 | Remy
Presentation preparation | 2015-11-05 | 2015-11-20 | 10 | Remy
Final Presentation | 2015-11-20 | 2015-11-20 | 2 | Remy
UAT Meeting Review | 2015-11-10 | 2015-11-10 | 8 | Remy
Test development case | 2015-11-05 | 2015-11-07 | 2 | Remy
Code Review | 2015-11-13 | 2015-11-13 | 2 | Remy
Review Of Iteration | 2015-11-13 | 2015-11-13 | 1 | Remy
Coding
Changes for UAT: |  |  | 16 | Jennifer, Amos, Chu Qian, Shing Hei
Bootstrap | 2015-11-06 | 2015-11-12 | 3 | Jennifer, Amos
Top K | 2015-11-06 | 2015-11-12 | 2 | Chu Qian, Shing Hei
Basic App Usage | 2015-11-06 | 2015-11-12 | 2 | Chu Qian, Shing Hei
Heat Map | 2015-11-06 | 2015-11-12 | 3 | Jennifer, Amos
Smart phone Overuse & Advanced | 2015-11-06 | 2015-11-12 | 4 | Chu Qian, Shing Hei
Social Activeness | 2015-11-06 | 2015-11-12 | 2 | Jennifer, Amos
Integration, testing/debug, Documentation, Deployment |  |  | 12 | Jennifer, Amos, Chu Qian, Shing Hei
Bootstrap | 2015-11-12 | 2015-11-13 | 3 | Jennifer, Amos
Top K | 2015-11-12 | 2015-11-13 | 1 | Chu Qian, Shing Hei
Basic App Usage | 2015-11-12 | 2015-11-13 | 2 | Chu Qian, Shing Hei
Heat Map | 2015-11-12 | 2015-11-13 | 2 | Jennifer, Amos
Smart phone Overuse & Advanced | 2015-11-12 | 2015-11-13 | 2 | Chu Qian, Shing Hei
Social Activeness | 2015-11-12 | 2015-11-13 | 2 | Jennifer, Amos