## Slide 1: Supervisor Meeting 1
PONG PONG
Team 4
AMOS TAN | JENNIFER YAP|KOH CHU QIAN | REMY NG | TANG SHING HEI

## Slide 2
  Overall Schedule
  Milestones
  Iterations
Content Page

## Slide 3: Overall Schedule
10 days | 9 days | 9 days | 12 days | 7 days | Buffer | 9 days
58 hours | 50 hours | 48 hours | 44 hours | 31 hours | 3 days | 57 hours
START
END
Iteration 1
Iteration 2
Iteration 3
Iteration 4
Iteration 5
Iteration 6
WEEK
5
7
8
9
11
12
14

## Slide 4: Overall Schedule
Iteration | Start | End | PM | Pair 1 | Pair 2 | Total Days
Iteration 1 (Week 5-7) | 18 September | 27 September | Chu Qian | Remy & Jennifer | Amos & Shing Hei | 10 days
Iteration 2 (Week 7-8) | 28 September | 6 October | Remy | Amos & Chu Qian | Jennifer & Shing Hei | 9 days
Iteration 3 (Week 8-9) | 7 October | 15 October | Jennifer | Remy & Chu Qian | Amos & Shing Hei | 9 days
Iteration 4 (Week 9-11) | 16 October | 27 October | Shing Hei | Amos & Remy | Chu Qian & Jennifer | 12 days
Iteration 5 (Week 11-12) | 28 October | 3 November | Amos | Remy & Shing Hei | Jennifer & Chu Qian | 7 days
Buffer | 3 November | 5 November |  |  |  | 3 days
Iteration 6 (Week 12-14) | 5 November | 20 November | Remy | Amos & Jennifer | Shing Hei & Chu Qian | 16 days

## Slide 5: Milestones
PM Review
Supervisor
Meeting 1
Supervisor
Meeting 2
Supervisor
Meeting 3
User Acceptance Test
Final Presentation
WEEK
5
7
8
9
11
13

## Slide 6: Iteration 1
Research
Test Deployment Case
Bootstrap
Integration, testing, documentation, Deployment
Supervisor Meeting Review
Review of iteration
Login
Diagrams
2 hour
11 hour
2 hour
2 hour
8 hour
Bootstrap
3 hour
23 hour
5 hour
3 hour
Pair 1: Amos & Shing Hei
Pair 2: Remy & Jennifer
START
END
Critical Path:

## Slide 7
Iteration 2
Research
Test Deployment Case
Basic App Usage Report
PM Review
Top-K App Usage Report
UI Design & Diagrams
2 hour
5 hour
2 hour
2 hour
7 hour
SmartPhone Overuse Report
6 hour
13 hour
3 hour
Pair 1: Jennifer & Shing Hei
Pair 2: Amos & Chu Qian
START
Review of iteration
Integration, testing, documentation, Deployment
END
Critical Path:
Top-K App Usage & Smartphone
6 hour
consists of
Basic App Report
4 hour
consists of

## Slide 8
Iteration 3
Research
Test Deployment Case
Smartphone Usage Heat-map
Supervisor Meeting Review
Loading Location Data
UI Design & Diagrams
2 hour
3 hour
2 hour
2 hour
10 hour
Deletion of Location Data
5 hour
5 hour
12 hour
3 hour
Pair 1: Chu Qian & Remy
Pair 2: Amos & Shing Hei
START
Review of iteration
Social Activeness
5 hour
Integration, testing, documentation, Deployment
END
Critical Path:

## Slide 9
Iteration 4
Research
Test Deployment Case
Advanced Smartphone Overuse Report
Supervisor Meeting
Graphical UIs (HeatMap & Chart)
UI Design & Diagrams
2 hour
3 hour
2 hour
2 hour
12 hour
9 hour
11 hour
3 hour
Pair 1: Amos & Remy
Pair 2: Chu Qian & Jennifer
START
Review of iteration
Integration, testing, documentation, Deployment
END
Critical Path:

## Slide 10
Iteration 5
Research & Diagram
Test Deployment Case
Optimise Basic App Usage, Heatmap
Optimise Bootstrap, Top K
2 hour
2 hour
5 hour
4 hour
10 hour
3 hour
Pair 1: Jennifer & Chu Qian
Pair 2: Remy & Shing Hei
START
Review of iteration
Integration, testing, documentation, Deployment
END
Optimise Smartphone, Social Activeness
Critical Path:
5 hour

## Slide 11
Iteration 6
Research & Diagram
Test Deployment Case
UAT Changes: Top K, Basic App Usage, Smartphone
UAT Changes: Bootstrap, HeatMap, Social Activeness
4 hour
2 hour
8 hour
8 hour
3 hour
Pair 1: Jennifer & Amos
Pair 2: Chu Qian & Shing Hei
START
Review of iteration
Integration, testing, documentation, Deployment
END
UAT Review
8 hour
Bootstrap, HeatMap, Social Activeness
7 hour
Top K, Basic App Usage, Smartphone
5 hour
consists of
consists of
Critical Path:

## Slide 12
Q & A

## Slide 13
THANK YOU