## Slide 1: Supervisor Meeting 3
PONG PONG
Team 4
AMOS TAN | JENNIFER YAP|KOH CHU QIAN | REMY NG | TANG SHING HEI

## Slide 2
  Overall Schedule
  Programming Hours
  Iterations
  Milestones
  Iteration 3 Review
  Iteration 4
Content Page

## Slide 3: Overall Schedule
Iteration | Start | End | Total Days
Iteration 1 (Week 5 – Week 7) | 17 September | 27 September | 11 days
 | 17 September | 30 September | 14 days
Iteration 2 (Week 7 – Week 8) | 1 October | 8 October | 8 days
 | 1 October | 9 October | 9 days
Iteration 3 (Week 8 – Week 10) | 9 October | 19 October | 11 days
 | 9 October | 21 October | 13 days
Iteration 4 (Week 10 – Week 11) | 22 October | 29 October | 8 days
Iteration 5 (Week 11 – Week 12) | 29 October | 7 November | 10 days
Iteration 6 (Week 12 – Week 14) | 7 November | 18 November | 12 days
Buffer Days (for presentation) | 19 November | 20 November | 2 days

## Slide 4: Overall Schedule
14 days |  | 9 days |  | 13 days |  | 10 days |  | 10 days |  | 12 days |  | Buffer
64.85 hours |  | 83.67 hours |  | 82.34 hours |  | 86 hours |  | 70 hours |  | 33 hours |  | 2 days
P | NP | P | NP | P | NP | P | NP | P | NP | P | NP | 
46.35 | 18.5 | 72.67 | 11 | 63.84 | 18.5 | 67 | 19 | 52 | 18 | 25 | 8 | 
START
END
Iteration 1
Iteration 2
Iteration 3
Iteration 4
Iteration 5
Iteration 6
WEEK
5
7
8
10
11
12
14
Legend:
P  Programming
NP  Non-programming

## Slide 5: Programming Hours
 | Jennifer | Amos | Shing Hei | Remy | Chu Qian
Iteration 1 | 29.85 | 16.5 | 16.5 | 29.85 | 
Iteration 2 | 38.58 | 34.09 | 38.58 |  | 34.09
Iteration 3 |  | 31.97 | 31.97 | 31.87 | 31.87
Iteration 4 | 30 | 37 |  | 37 | 30
Iteration 5 | 22 |  | 30 | 30 | 22
Iteration 6 | 10 | 10 | 15 |  | 15
Total | 130.43 | 129.56 | 132.05 | 128.72 | 132.96
Notes: Standard deviation of 13.0744 hours

## Slide 6: Milestones
PM Review
Supervisor
Meeting 1
Supervisor
Meeting 2
Supervisor
Meeting 3
User Acceptance Test
Final Presentation
WEEK
5
7
8
10
11
13
Chu Qian
Remy
Jennifer
Shing Hei
Amos
Remy
14

## Slide 7: Planned Iterations
 | Tasks
Iteration 1 | Bootstrap and Login Functionality
Iteration 2 | Basic App Reports, Top-K and Smartphone Overuse Report
Iteration 3 | Loading/Deleting Location data, Heatmap, Social Activeness Report
Iteration 4 | Graphical UIs, Advanced Smartphone Overuse Report, Changes to reflect Wiki requirements & Code Clean-up
Iteration 5 | Optimisation of functionalities & Code Clean-up
Iteration 6 | Improvements of functions after UAT

## Slide 8: Role Rotation
 | PM | Pair 1 | Pair 2
Iteration 1 | Chu Qian | Remy & Jennifer | Amos & Shing Hei
Iteration 2 | Remy | Amos & Chu Qian | Jennifer & Shing Hei
Iteration 3 | Jennifer | Remy & Chu Qian | Amos & Shing Hei
Iteration 4 | Shing Hei | Amos & Remy | Chu Qian & Jennifer
Iteration 5 | Amos | Remy & Shing Hei | Jennifer & Chu Qian
Iteration 6 | Remy | Amos & Jennifer | Shing Hei & Chu Qian

## Slide 9: Iteration Overview

## Slide 10: Iteration 1
Research
Test Deployment Case
Bootstrap
Integration, Testing, Documentation, Deployment
Supervisor Meeting Review
Review of iteration
Login
Diagrams
1 Day
2 Days
1 Day
1 Day
2 Days
Bootstrap
1 Day
5 Days
2 Days
Pair 1: Amos & Shing Hei
Pair 2: Remy & Jennifer
START
END
Critical Path:
11 Days

## Slide 11
Iteration 2
Research
Test Deployment Case
Basic App Usage Report
PM Review
Top-K App Usage Report
UI Design & Diagrams
1 Day
1 Day
3 Days
SmartPhone Overuse Report
2 Days
2 Days
1 Day
Pair 1: Jennifer & Shing Hei
Pair 2: Amos & Chu Qian
START
Review of iteration
Integration, Testing, Documentation, Deployment, Regression Testing
END
Critical Path:
Top-K App Usage & Smartphone
1 Day
consists of
Basic App Report
1 Day
consists of
8 Days

## Slide 12
Iteration 3
Research
Test Deployment Case
Smartphone Usage Heat-map
Loading Location Data
UI Design & Diagrams
1 Day
3 Days
Deletion of Location Data
1 Day
3 Days
1 Day
Pair 1: Chu Qian & Remy
Pair 2: Amos & Shing Hei
START
Review of iteration
Social Activeness
2 Days
Integration, Testing, Documentation, Deployment, Regression Testing
END
Critical Path:
2 Days
11 Days
3 Days
Supervisor Meeting Review

## Slide 13
Pair 1: Chu Qian & Jennifer
Iteration 4
Pair 2: Amos & Remy
Test Deployment Case
Review of Diagrams
Research
Advanced Smartphone Overuse Report, Changes to reflect Wiki requirements &
Code Clean-up
Supervisor Meeting
Graphical UIs (Heatmap & Chart), Change to reflect Wiki requirements
3 Days
3 Days
4 Days
START
Review of iteration
Integration, Testing, Documentation, Deployment, Regression Testing
END
Critical Path:
1 Day
8 Days
Ad-hoc Meeting to discuss Wiki changes
UI Planning

## Slide 14
Pair 1: Jennifer & Chu Qian
Iteration 5
Review of iteration
Research & Diagram
Test Deployment Case
Optimise Bootstrap, Top K &
Code Clean-up
1 Day
1 Day
2 Days
5 Days
Pair 2: Remy & Shing Hei
START
Integration, Testing, Documentation, Deployment, Regression Testing
END
Optimise Basic App Usage, Heatmap
Smartphone, Social Activeness & Code Clean-up
Critical Path:
3 Days
10 Days
UAT Review

## Slide 15
Iteration 6
Review of iteration
Research & Diagram
Test Deployment Case
UAT Changes: Top K, Basic App Usage, Smartphone
UAT Changes: Bootstrap, HeatMap, Social Activeness
3 Days
2 Days
1 Day
Pair 1: Jennifer & Amos
Pair 2: Chu Qian & Shing Hei
START
END
UAT Review
1 Day
Bootstrap, HeatMap, Social Activeness
1 Day
Top K, Basic App Usage, Smartphone
1 Day
consists of
consists of
Critical Path:
Integration, testing, documentation, Deployment, Regression Testing
1 Day
12 Days
Final Presentation Preparation
6 Days

## Slide 16: Iteration 3 Review

## Slide 17: Schedule Metrics
Iteration | Planned | Actual | Schedule Metrics
1 | 11 Days | 14 Days | 0.79
2 | 8 Days | 9 Days | 0.88
3 | 11 Days | 13 Days | 0.84

## Slide 18: Iteration 3 Metrics
Planned Iteration Dates: 09/10/2015 – 19/10/2015
Actual Iteration Dates: 09/10/2015 – 21/10/2015
Delay was due to the overrun of most pair programming sessions
Schedule Metrics at 0.84
  Schedule was delayed by 2 days due to feature update in wiki for Social Activeness Report towards the end of iteration 3
  Results in incomplete functionality
  Feature-boxers: Decided to complete the function before moving forward
  Buffer Days: Drops to 2 days for final presentation
Current Bug Metrics Value = 0

## Slide 19: Learning Points
Allocate buffer time in between back-to-back tasks to prevent mass rescheduling of Pair Programming Log
Ensure schedule planned dates are closely adhered to

## Slide 20: Iteration 3
Project Manager: Shing Hei
Pair Programmers:
  Remy & Amos
  Jennifer & Chu Qian
Planning phase is done
Pair programming sessions started for
  Advanced Smartphone Overuse Report
  Graphical UIs (Heatmap and Chart)

## Slide 21
Q & A

## Slide 22
THANK YOU