## Sheet1
S/N | Issuer | Issue Date | Commits | Resolve Date | Status | Functionality | Description | Severity | Priority | Mitigation | Assigned To
1 | Shing Hei | 27/9/2015 | 5f7c2db6 | 28/9/2015 | Fixed | Bootstrap | When user key in .../bootstrap directly at the launch of the application, user did not get redirected back to login | 5 | Mid | Immediately | Remy, Jennifer
2 | Remy | 27/9/2015 | 24935de9 | 28/9/2015 | Fixed | Bootstrap | Success message not shown when uploaded the csv files | 5 | High | Immediately | Remy, Jennifer
3 | Remy | 28/9/2015 | b5c3c4bd |  | Ignored | Bootstrap | Error messages are displayed together with an additional string of output | 1 | Mid | Resolve during iteration 2 | Amos, Chuqian
4 | Remy | 28/9/2015 | b5c3c4bd |  | Ignored | Bootstrap | JSON Bootstrap function does not carry out common validations | 5 | Mid | Resolve during iteration 2 | Amos, Chuqian