## Sheet1
S/N | Issuer | Issue Date | Commits | Resolve Date | Status | Functionality | Description | Severity | Priority | Mitigation | Assigned To
1 | Shing Hei | 27/9/2015 | 5f7c2db6 | 28/9/2015 | Fixed | Bootstrap | When user key in .../bootstrap directly at the launch of the application, user did not get redirected back to login | 5 | Mid | Immediately | Remy, Jennifer
2 | Remy | 27/9/2015 | 24935de9 | 28/9/2015 | Fixed | Bootstrap | Success message not shown when uploaded the csv files | 5 | High | Immediately | Remy, Jennifer
3 | Remy | 28/9/2015 | b5c3c4bd | 29/9/2015 | Resolve Immediately | Bootstrap | Error messages are displayed together with an additional string of output | 1 | Mid | Resolve Immediately | Remy, Jennifer
4 | Remy | 28/9/2015 | b5c3c4bd | 29/9/2015 | Resolve Immediately | Bootstrap | JSON Bootstrap function does not carry out common validations | 5 | Mid | Resolve Immediately | Remy, Jennifer
5 | Remy | 28/9/2015 | b5c3c4bd | 29/9/2015 | Resolve Immediately | Bootstrap | Incorrect line number output to bootstrap UI for duplicate rows | 5 | High | Resolve Immediately | Remy, Jennifer
6 | Remy | 29/9/2015 |  | 9/10/2015 | Resolve in Iteration 2 | Login | JSON field is incorrectly named | 1 | Mid | Resolve in Iteration 2 | Jennifer, Shing Hei
7 | Remy | 29/9/2015 |  | 9/10/2015 | Resolve in Iteration 2 | Bootstrap | Common validation for Bootstrap error message is incorrectly named | 1 | Mid | Resolve in iteration 2 | Jennifer, Shing Hei
8 | Amos | 8/10/2015 |  | 9/10/2015 | Resolve Immediately | BasicAppUsage | LinkedHashMap.replace() method not found in jdk 1.7 | 5 | Mid | Resolve in Iteration 2 | Amos, Chu Qian
9 | Amos | 8/10/2015 |  | 9/10/2015 | Resolve Immediately | BasicAppUsage | Total usage time for BasicAppUsage breakdown returns incorrect value | 5 | Mid | Resolve in iteration 2 | Amos, Chu Qian
10 | Amos | 9/10/2015 |  |  |  | BasicAppUsage | Basic App Breakdown by app category does not show error message for invalid date. | 1 | Low | Resolve in iteration 3