## Sheet1
S/N | Issuer | Issue Date | Resolve Date | Status | Functionality | Description | Severity | Priority | Mitigation | Assigned To
1 | Shing Hei | 27/9/2015 | 28/9/2015 | Fixed | Bootstrap | When user key in .../bootstrap directly at the launch of the application, user did not get redirected back to login | 5 | Mid | Immediately | Remy, Jennifer
2 | Remy | 27/9/2015 | 28/9/2015 | Fixed | Bootstrap | Success message not shown when uploaded the csv files | 5 | High | Immediately | Remy, Jennifer
3 | Remy | 28/9/2015 | 29/9/2015 | Resolve Immediately | Bootstrap | Error messages are displayed together with an additional string of output | 1 | Mid | Resolve Immediately | Remy, Jennifer
4 | Remy | 28/9/2015 | 29/9/2015 | Resolve Immediately | Bootstrap JSON | JSON Bootstrap function does not carry out common validations | 5 | Mid | Resolve Immediately | Remy, Jennifer
5 | Remy | 28/9/2015 | 29/9/2015 | Resolve Immediately | Bootstrap | Incorrect line number output to bootstrap UI for duplicate rows | 5 | High | Resolve Immediately | Remy, Jennifer
6 | Remy | 29/9/2015 | 9/10/2015 | Resolve in Iteration 2 | Login JSON | JSON field is incorrectly named | 1 | Mid | Resolve in Iteration 2 | Jennifer, Shing Hei
7 | Remy | 29/9/2015 | 9/10/2015 | Resolve in Iteration 2 | Bootstrap | Common validation for Bootstrap error message is incorrectly named | 1 | Mid | Resolve in iteration 2 | Jennifer, Shing Hei
8 | Amos | 8/10/2015 | 9/10/2015 | Resolve Immediately | BasicAppUsage | LinkedHashMap.replace() method not found in jdk 1.7 | 5 | Mid | Resolve in Iteration 2 | Amos, Chu Qian
9 | Amos | 8/10/2015 | 9/10/2015 | Resolve Immediately | BasicAppUsage | Total usage time for BasicAppUsage breakdown returns incorrect value | 5 | Mid | Resolve in iteration 2 | Amos, Chu Qian
10 | Amos | 9/10/2015 | 19/10/2015 | Fixed | BasicAppUsage | Basic App Breakdown by app category does not show error message for invalid date. | 1 | Low | Resolve in iteration 3 | Remy, Chu Qian
11 | Remy | 19/10/2015 | 19/10/2015 | Fixed | Login JSON | Login JSON did not display error messages correctly | 1 | High | Resolve Immediately | Remy, Chu Qian
12 | Remy | 19/10/2015 | 19/10/2015 | Fixed | BasicAppUsage | Percentage for all basic app usage reports not rounded to nearest integer | 1 | High | Resolve Immediately | Remy, Chu Qian
13 | Remy | 19/10/2015 | 19/10/2015 | Fixed | BasicAppUsage | Program crashes when invalid sort categories are typed into category under basic app usage breakdown by demographics | 10 | High | Resolve Immediately | Remy, Chu Qian
14 | Remy | 19/10/2015 | 19/10/2015 | Fixed | BasicAppUsage | Redid calculation for diurnal to include all users within the day | 5 | High | Resolve Immediately | Remy, Chu Qian
15 | Remy | 19/10/2015 | 19/10/2015 | Fixed | BasicAppUsage JSON | Basic App Usage JSON does not validate for invalid dates | 5 | High | Resolve Immediately | Remy, Chu Qian
16 | Remy | 19/10/2015 | 19/10/2015 | Fixed | BasicAppUsage JSON | Basic App Usage JSON breakdown by usage time category and demographics does not validate for invalid order and dates, hence causing the system to crash | 10 | High | Resolve Immediately | Remy, Chu Qian
17 | Remy | 19/10/2015 | 19/10/2015 | Fixed | BasicAppUsage JSON | Basic App Usage JSON Unable to validate for invalid dates and does not display JSON output for percentage in the correct format | 5 | Mid | Resolve Immediately | Remy, Chu Qian
18 | Chu Qian | 21/10/2015 | 21/10/2015 | Fixed | BasicAppUsage JSON | Basic App Usage Diurnal failed the common validation check in JSON. It does not checks for missing and blank filters and invalid token displayed twice. | 5 | Mid | Resolve Immediately | Remy, Chu Qian
19 | Chu Qian | 21/10/2015 | 21/10/2015 | Fixed | Top K App | All Top K App pages were redirected to Smartphone Overuse page | 1 | Low | Resolve Immediately | Remy, Chu Qian
20 | Chu Qian | 21/10/2015 | 21/10/2015 | Fixed | Top K App | All Top K App pages in UI did not prompt "Please enter a valid date" when user submitted empty dates | 1 | Low | Resolve Immediately | Remy, Chu Qian
21 | Chu Qian | 21/10/2015 | 21/10/2015 | Fixed | Top K App JSON | All Top K App crashes on empty attributes in JSON | 10 | High | Resolve Immediately | Remy, Chu Qian
22 | Chu Qian | 21/10/2015 | 21/10/2015 | Fixed | Top K App JSON | All Top K App did not show invalid start date/end date when we enter the incorrect date ranges and it does category instead of app category | 1 | Low | Resolve Immediately | Remy, Chu Qian
23 | Chu Qian | 21/10/2015 | 21/10/2015 | Fixed | Smartphone Overuse JSON | Smartphone Overuse fails the common validation check in JSON | 5 | Mid | Resolve Immediately | Remy, Chu Qian
24 | Chu Qian | 21/10/2015 | 21/10/2015 | Fixed | Smartphone Overuse | Smartphone Overuse report does not shows the results in seconds, duration is shown in hours for duration and access frequency is not shown correct to 2 decimal places | 10 | Mid | Resolve Immediately | Remy, Chu Qian
25 | Chu Qian | 21/10/2015 | 21/10/2015 | Fixed | Bootstrap | Bootstrap UI shows the incorrect error message for macaddress | 1 | Low | Resolve Immediately | Remy, Chu Qian
26 | Chu Qian | 21/10/2015 | 21/10/2015 | Fixed | Bootstrap JSON | Bootstrap JSON shows the wrong error message output, it should be message instead of messages. | 1 | Low | Resolve Immediately | Remy, Chu Qian
27 | Chu Qian | 21/10/2015 | 21/10/2015 | Fixed | BasicAppUsage | Basic App Usage by App Category does not display "Start date cannot be later than end Date" | 1 | Low | Resolve Immediately | Remy, Chu Qian
28 | Jennifer | 26/10/2015 |  | Resolve in Iteration 5 | Top K School | Result only displays SIS when there are supposed to also include other schools | 5 | Mid | Resolve in Iteration 5 | Jennifer, Chu Qian
29 | Chu Qian | 28/10/2015 | 28/10/2015 | Fixed | Location Delete UI | Valid startdate and endate but data was not successfully deleted | 1 | Low | Resolve Immediately | Jennifer, Chu Qian
30 | Chu Qian | 28/10/2015 | 28/10/2015 | Fixed | Location Delete UI | UI shows that location id is valid even though the location id is not found in database | 1 | Low | Resolve Immediately | Jennifer, Chu Qian
31 | Chu Qian | 28/10/2015 | 28/10/2015 | Fixed | Location Delete UI | UI does not display the error of enddate before startdate | 1 | Low | Resolve Immediately | Jennifer, Chu Qian
32 | Amos | 29/10/2015 | 29/10/2015 | Fixed | Top K Student | Index out of bounds for parameters (startdate: 06/04/2015, enddate: 06/04/2015 k: 10, cateogry: entertaintment) | 10 | High | Resolve Immediately | Amos, Remy
33 | Amos | 29/10/2015 | 29/10/2015 | Fixed | Top K Apps by App Category JSON | When no parameters are specified for the JSON call, the app crashes on NullPointerException | 10 | High | Resolve Immediately | Amos, Remy
34 | Amos | 29/10/2015 | 29/10/2015 | Fixed | Top K Student JSON | When no parameters are specified for the JSON call, the app crashes on NullPointerException | 10 | High | Resolve Immediately | Amos, Remy
35 | Amos | 29/10/2015 | 29/10/2015 | Fixed | Top K School JSON | When no parameters are specified for the JSON call, the app crashes on NullPointerException | 10 | High | Resolve Immediately | Amos, Remy
36 | Jennifer | 29/10/2015 | 29/10/2015 | Fixed | Login JSON | When full email is passed in with matching password, JSON displays success message | 1 | Low | Resolve Immediately | Jennifer, Chu Qian
37 | Amos | 29/10/2015 | 29/10/2015 | Fixed | Social Activeness Controller | Null pointer exception thrown when macAddress is valid but does not have any data associated with that mac address | 10 | High | Resolve Immediately | Amos, Remy
38 | Amos | 29/10/2015 | 29/10/2015 | Fixed | Open Csv plugin | Bootstrap not working properly after switching to open-csv-2.4 | 10 | high | Resolve Immediately | Amos, Remy
39 | Amos | 29/10/2015 | 29/10/2015 | Fixed | Smartphone Usage Heatmap | Report not showing all semantic places for floor selected | 5 | med | Resolve Immediately | Amos, Remy
40 | Amos | 29/10/2015 | 29/10/2015 | Fixed | Smartphone Usage Heatmap | Missing token validation not working. | 5 | med | Resolve Immediately | Amos, Remy