## Sheet1
S/N | Issuer | Issue Date | Resolve Date | Status | Functionality | Description | Severity | Priority | Mitigation | Assigned To
1 | Shing Hei | 27/9/2015 | 28/9/2015 | Fixed | Bootstrap | When user key in .../bootstrap directly at the launch of the application, user did not get redirected back to login | 5 | Mid | Immediately | Remy, Jennifer
2 | Remy | 27/9/2015 | 28/9/2015 | Fixed | Bootstrap | Success message not shown when uploaded the csv files | 5 | High | Immediately | Remy, Jennifer
3 | Remy | 28/9/2015 | 29/9/2015 | Fixed | Bootstrap | Error messages are displayed together with an additional string of output | 1 | Mid | Resolve Immediately | Remy, Jennifer
4 | Remy | 28/9/2015 | 29/9/2015 | Fixed | Bootstrap JSON | JSON Bootstrap function does not carry out common validations | 5 | Mid | Resolve Immediately | Remy, Jennifer
5 | Remy | 28/9/2015 | 29/9/2015 | Fixed | Bootstrap | Incorrect line number output to bootstrap UI for duplicate rows | 5 | High | Resolve Immediately | Remy, Jennifer
6 | Remy | 29/9/2015 | 9/10/2015 | Fixed | Login JSON | JSON field is incorrectly named | 1 | Mid | Resolve in Iteration 2 | Jennifer, Shing Hei
7 | Remy | 29/9/2015 | 9/10/2015 | Fixed | Bootstrap | Common validation for Bootstrap error message is incorrectly named | 1 | Mid | Resolve in iteration 2 | Jennifer, Shing Hei
8 | Amos | 8/10/2015 | 9/10/2015 | Fixed | BasicAppUsage | LinkedHashMap.replace() method not found in jdk 1.7 | 5 | Mid | Resolve in Iteration 2 | Amos, Chu Qian
9 | Amos | 8/10/2015 | 9/10/2015 | Fixed | BasicAppUsage | Total usage time for BasicAppUsage breakdown returns incorrect value | 5 | Mid | Resolve in iteration 2 | Amos, Chu Qian
10 | Amos | 9/10/2015 | 19/10/2015 | Fixed | BasicAppUsage | Basic App Breakdown by app category does not show error message for invalid date. | 1 | Low | Resolve in iteration 3 | Remy, Chu Qian
11 | Remy | 19/10/2015 | 19/10/2015 | Fixed | Login JSON | Login JSON did not display error messages correctly | 1 | High | Resolve Immediately | Remy, Chu Qian
12 | Remy | 19/10/2015 | 19/10/2015 | Fixed | BasicAppUsage | Percentage for all basic app usage reports not rounded to nearest integer | 1 | High | Resolve Immediately | Remy, Chu Qian
13 | Remy | 19/10/2015 | 19/10/2015 | Fixed | BasicAppUsage | Program crashes when invalid sort categories are typed into category under basic app usage breakdown by demographics | 10 | High | Resolve Immediately | Remy, Chu Qian
14 | Remy | 19/10/2015 | 19/10/2015 | Fixed | BasicAppUsage | Redid calculation for diurnal to include all users within the day | 5 | High | Resolve Immediately | Remy, Chu Qian
15 | Remy | 19/10/2015 | 19/10/2015 | Fixed | BasicAppUsage JSON | Basic App Usage JSON does not validate for invalid dates | 5 | High | Resolve Immediately | Remy, Chu Qian
16 | Remy | 19/10/2015 | 19/10/2015 | Fixed | BasicAppUsage JSON | Basic App Usage JSON breakdown by usage time category and demographics does not validate for invalid order and dates, hence causing the system to crash | 10 | High | Resolve Immediately | Remy, Chu Qian
17 | Remy | 19/10/2015 | 19/10/2015 | Fixed | BasicAppUsage JSON | Basic App Usage JSON Unable to validate for invalid dates and does not display JSON output for percentage in the correct format | 5 | Mid | Resolve Immediately | Remy, Chu Qian
18 | Chu Qian | 21/10/2015 | 21/10/2015 | Fixed | BasicAppUsage JSON | Basic App Usage Diurnal failed the common validation check in JSON. It does not checks for missing and blank filters and invalid token displayed twice. | 5 | Mid | Resolve Immediately | Remy, Chu Qian
19 | Chu Qian | 21/10/2015 | 21/10/2015 | Fixed | Top K App | All Top K App pages were redirected to Smartphone Overuse page | 1 | Low | Resolve Immediately | Remy, Chu Qian
20 | Chu Qian | 21/10/2015 | 21/10/2015 | Fixed | Top K App | All Top K App pages in UI did not prompt "Please enter a valid date" when user submitted empty dates | 1 | Low | Resolve Immediately | Remy, Chu Qian
21 | Chu Qian | 21/10/2015 | 21/10/2015 | Fixed | Top K App JSON | All Top K App crashes on empty attributes in JSON | 10 | High | Resolve Immediately | Remy, Chu Qian
22 | Chu Qian | 21/10/2015 | 21/10/2015 | Fixed | Top K App JSON | All Top K App did not show invalid start date/end date when we enter the incorrect date ranges and it does category instead of app category | 1 | Low | Resolve Immediately | Remy, Chu Qian
23 | Chu Qian | 21/10/2015 | 21/10/2015 | Fixed | Smartphone Overuse JSON | Smartphone Overuse fails the common validation check in JSON | 5 | Mid | Resolve Immediately | Remy, Chu Qian
24 | Chu Qian | 21/10/2015 | 21/10/2015 | Fixed | Smartphone Overuse | Smartphone Overuse report does not shows the results in seconds, duration is shown in hours for duration and access frequency is not shown correct to 2 decimal places | 10 | Mid | Resolve Immediately | Remy, Chu Qian
25 | Chu Qian | 21/10/2015 | 21/10/2015 | Fixed | Bootstrap | Bootstrap UI shows the incorrect error message for macaddress | 1 | Low | Resolve Immediately | Remy, Chu Qian
26 | Chu Qian | 21/10/2015 | 21/10/2015 | Fixed | Bootstrap JSON | Bootstrap JSON shows the wrong error message output, it should be message instead of messages. | 1 | Low | Resolve Immediately | Remy, Chu Qian
27 | Chu Qian | 21/10/2015 | 21/10/2015 | Fixed | BasicAppUsage | Basic App Usage by App Category does not display "Start date cannot be later than end Date" | 1 | Low | Resolve Immediately | Remy, Chu Qian
28 | Jennifer | 26/10/2015 | 1/11/2015 | Fixed | Top K School | Result only displays SIS when there are supposed to also include other schools | 5 | Mid | Resolve Immediately | Shing Hei, Remy
29 | Chu Qian | 28/10/2015 | 28/10/2015 | Fixed | Location Delete UI | Valid startdate and endate but data was not successfully deleted | 1 | Low | Resolve Immediately | Jennifer, Chu Qian
30 | Chu Qian | 28/10/2015 | 28/10/2015 | Fixed | Location Delete UI | UI shows that location id is valid even though the location id is not found in database | 1 | Low | Resolve Immediately | Jennifer, Chu Qian
31 | Chu Qian | 28/10/2015 | 28/10/2015 | Fixed | Location Delete UI | UI does not display the error of enddate before startdate | 1 | Low | Resolve Immediately | Jennifer, Chu Qian
32 | Amos | 29/10/2015 | 29/10/2015 | Fixed | Top K Student | Index out of bounds for parameters (startdate: 06/04/2015, enddate: 06/04/2015 k: 10, cateogry: entertaintment) | 10 | High | Resolve Immediately | Amos, Remy
33 | Amos | 29/10/2015 | 29/10/2015 | Fixed | Top K Apps by App Category JSON | When no parameters are specified for the JSON call, the app crashes on NullPointerException | 10 | High | Resolve Immediately | Amos, Remy
34 | Amos | 29/10/2015 | 29/10/2015 | Fixed | Top K Student JSON | When no parameters are specified for the JSON call, the app crashes on NullPointerException | 10 | High | Resolve Immediately | Amos, Remy
35 | Amos | 29/10/2015 | 29/10/2015 | Fixed | Top K School JSON | When no parameters are specified for the JSON call, the app crashes on NullPointerException | 10 | High | Resolve Immediately | Amos, Remy
36 | Jennifer | 29/10/2015 | 29/10/2015 | Fixed | Login JSON | When full email is passed in with matching password, JSON displays success message | 1 | Low | Resolve Immediately | Jennifer, Chu Qian
37 | Amos | 29/10/2015 | 29/10/2015 | Fixed | Social Activeness Controller | Null pointer exception thrown when macAddress is valid but does not have any data associated with that mac address | 10 | High | Resolve Immediately | Amos, Remy
38 | Amos | 29/10/2015 | 29/10/2015 | Fixed | Open Csv plugin | Bootstrap not working properly after switching to open-csv-2.4 | 10 | High | Resolve Immediately | Amos, Remy
39 | Amos | 29/10/2015 | 29/10/2015 | Fixed | Smartphone Usage Heatmap | Report not showing all semantic places for floor selected | 5 | Med | Resolve Immediately | Amos, Remy
40 | Amos | 29/10/2015 | 29/10/2015 | Fixed | Smartphone Usage Heatmap | Missing token validation not working. | 5 | Med | Resolve Immediately | Amos, Remy
41 | Jennifer | 1/11/2015 | 1/11/2015 | Fixed | Bootstrap | Both invalid mac address and no matching mac address messages are displayed together | 5 | Med | Resolve Immediately | Jennifer, Chu Qian
42 | Shing Hei | 1/11/2015 | 1/11/2015 | Fixed | Top K | JSON validation fail to account for startdate being after enddate | 1 | Low | Resolve Immediately | Shing Hei, Remy
43 | Shing Hei | 2/11/2015 | 2/11/2015 | Fixed | Basic App Usage | Basic App Usage Report(Breakdown by usage time category and demographics) produces report even when none of the field is selected | 5 | Med | Resolve Immediately | Shing Hei, Remy
44 | Remy | 2/11/2015 | 2/11/2015 | Fixed | Basic App Usage | Basic App Usage Report JSON (Breakdown by usage time category and demographics) displays duplicate error message for invalid date | 1 | Low | Resolve Immediately | Shing Hei, Remy
45 | Remy | 2/11/2015 | 2/11/2015 | Fixed | Basic App Usage | Basic App Usage Report JSON reports displays invalid error message for token validation | 5 | Med | Resolve Immediately | Shing Hei, Remy
46 | Remy | 2/11/2015 | 2/11/2015 | Fixed | Basic App Usage | Basic App Usage Report(Diurnal pattern of app usage time) JSON output displays time up to the seconds between diurnal time range | 5 | Med | Resolve Immediately | Shing Hei, Remy
47 | Remy | 2/11/2015 | 2/11/2015 | Fixed | Basic App Usage | Basic App Usage JSON function-specific error messages are not being returned in the order as defined in the tables. Currently, all JSON messages sorted in alphabetical order | 10 | High | Resolve Immediately | Shing Hei, Remy
48 | Remy | 2/11/2015 | 2/11/2015 | Fixed | Basic App Usage | Basic App Usage Report JSON (Breakdown by usage time category and demographics) displays duplicate CCA options at the "Click Me to breakdown" option | 5 | Med | Resolve Immediately | Shing Hei, Remy
49 | Remy | 2/11/2015 | 2/11/2015 | Fixed | All except BAU and Advanced Smartphone Overuse | JSON function-specific error messages are not being returned in the order as defined in the tables. Currently, all JSON messages sorted in alphabetical order | 10 | High | Scheduled to next PP session | Shing Hei, Remy
50 | Jennifer | 3/11/2015 | 3/11/2015 | Fixed | Social Activeness | Report displays negative percentage | 5 | Med | Resolve Immediately | Jennifer, Chu Qian
51 | Jennifer | 3/11/2015 | 3/11/2015 | Fixed | Social Activeness | Invalid error messages for JSON validation | 1 | Low | Resolve Immediately | Jennifer, Chu Qian
52 | Jennifer | 3/11/2015 | 3/11/2015 | Fixed | Location Delete UI | Validation of input was wrong for location ID and semantic place | 5 | Med | Resolve Immediately | Jennifer, Chu Qian
53 | Jennifer | 3/11/2015 | 3/11/2015 | Fixed | Location Delete UI | JSON error messages not in order | 5 | Med | Resolve Immediately | Jennifer, Chu Qian
54 | Jennifer | 3/11/2015 | 3/11/2015 | Fixed | Location Delete UI | Start date and end date logic was incorrect | 5 | Med | Resolve Immediately | Jennifer, Chu Qian
55 | Chu Qian | 3/11/2015 | 3/11/2015 | Fixed | Smartphone overuse JSON | The JSON validation output was in the wrong sequence | 5 | Med | Resolve Immediately | Jennifer, Chu Qian
56 | Remy | 3/11/2015 | 3/11/2015 | Fixed | Basic App Usage Breakdown by Demographics and Time Usage | Used wrong List of data to breakdown by CCA | 5 | Med | Resolve Immediately | Shing Hei, Remy
57 | Shing Hei | 4/11/2015 | 4/11/2015 | Fixed | Location Delete | Location Delete JSON crashes for token input only. Requests for startdate as a required input | 10 | High | Resolve Immediately | Shing Hei, Remy
58 | Chu Qian | 4/11/2015 | 4/11/2015 | Fixed | Smartphone overuse UI | The UI table is not reflecting the correct usage and access frequency | 5 | Med | Resolve Immediately | Amos, Chu Qian
59 | Shing Hei | 4/11/2015 | 4/11/2015 | Fixed | Smartphone Usage Heatmap | Smartphone Usage Heatmap UI is cut off at the bottom of the screen | 1 | Low | Resolve Immediately | Shing Hei, Remy
60 | Amos | 6/11/2015 | 11/11/2015 | Fixed | Basic App Usage , Breakdown by app category | output for UAT do not reflect accordingly | 1 | Low | Resolve in iteration 6, immediately | Shing Hei, Chu Qian
61 | Amos | 6/11/2015 | 11/11/2015 | Fixed | Basic App Usage, Diurnal | output for UAT do not reflect accordingly | 1 | Low | Resolve in iteration 6, immediately | Shing Hei, Chu Qian
62 | Amos | 6/11/2015 | 12/11/2015 | Fixed | Location Upload | Crash on loading location data | 10 | High | Resolve in iteration 6, immediately | Shing Hei, Chu Qian
63 | Amos | 6/11/2015 | 12/11/2015 | Fixed | Delete Location Data | Deleted reccord output do not reflect accordingly | 1 | Low | Resolve in iteration 6, immediately | Shing Hei, Chu Qian
64 | Amos | 6/11/2015 | 10/11/2015 | Fixed | Advanced Overuse Report | Output for UAT do not reflect accordingly | 1 | Low | Resolve in iteration 6, immediately | Amos, Jennifer
65 | Amos | 6/11/2015 | 12/11/2015 | Fixed | Bootstrap | Validation output does not reflect accordingly | 1 | Low | Resolve in iteration 6, immediately | Shing Hei, Chu Qian
66 | Amos | 6/11/2015 | 12/11/2015 | Fixed | Bootstrap | Boostrap times out on large file | 10 | High | Resolve in iteration 6, immediately | Shing Hei, Chu Qian
67 | Remy | 11/11/2015 | 13/11/2015 | Fixed | Top K App JSON | field name should be app-name instead of name | 1 | Low | Resolve in iteration 6, immediately | Shing Hei, Chu Qian
68 | Remy | 11/11/2015 | 11/11/2015 | Fixed | Basic App breakdown by Demographics JSON | Output for breakdown is not in ascending order. Percentage should also be an integer. | 5 | Medium | Resolve Immediately | Shing Hei, Chu Qian
69 | Remy | 11/11/2015 | 11/11/2015 | Fixed | Basic App App Category JSON | Not all categories are displayed. | 5 | Low | Resolve Immediately | Shing Hei, Chu Qian
70 | Remy | 11/11/2015 | 11/11/2015 | Fixed | Basic App Breakdown by App Category JSON | Categories are not displayed in ascending order. | 5 | Medium | Resolve Immediately | Shing Hei, Chu Qian
71 | Remy | 11/11/2015 | 11/11/2015 | Fixed | Basic App Breakdown by App Category JSON | Issues with rounding that causes percentage to be displayed wrongly | 1 | Low | Resolve Immediately | Shing Hei, Chu Qian
72 | Remy | 11/11/2015 | 11/11/2015 | Fixed | Basic App Diurnal Pattern JSON | Calculation for diurnal pattern is off | 5 | Medium | Resolve Immediately | Shing Hei, Chu Qian
73 | Remy | 11/11/2015 | 12/11/2015 | Fixed | Upload Additional Data JSON | When uploading additional data, file name with records loaded is not shown | 1 | Low | Resolve Immediately | Shing Hei, Chu Qian
74 | Remy | 11/11/2015 | 12/112015 | Fixed | Upload Additional Data JSON | Location Delete JSON is not shown | 1 | Low | Resolve Immediately | Shing Hei, Chu Qian
75 | Remy | 11/11/2015 | 12/11/2015 | Fixed | Bootstrap JSON | Invalid token is shown when token is supposed to be valid | 10 | High | Resolve Immediately | Shing Hei, Chu Qian
76 | Remy | 11/11/2015 | 13/11/2015 | Fixed | Advanced Smartphone Overuse Report JSON | Numbers are output in String format instead of as a number | 1 | Low | Resolve Immediately | Shing Hei, Chu Qian
77 | Shing Hei | 12/11/2015 | 12/11/2015 | Fixed | Bootstrap UI | Crash on empty app-id in app.csv | 10 | High | Resolve Immediately | Shing Hei, Chu Qian
78 | Chu Qian | 12/11/2015 | 12/11/2015 | Fixed | Bootstrap | Bootstrap crashes on invalid token | 10 | High | Resolve Immediately | Shing Hei, Chu Qian
79 | Chu Qian | 12/11/2015 | 12/11/2015 | Fixed | Bootstrap | Bootstrap does not shows the correct output for the error messages | 5 | Medium | Resolve Immediately | Shing Hei, Chu Qian
80 | Chu Qian | 12/112015 | 12/11/2015 | Fixed | Bootstrap Location Delete | User token can be used to bootstrap data | 5 | Medium | Resolve Immediately | Shing Hei, Chu Qian
81 | Chu Qian | 12/11/2015 | 12/11/2015 | Fixed | Location Delete | User is not able to key in seconds for endtime and starttime fields | 5 | Medium | Resolve Immediately | Shing Hei, Chu Qian
82 | Chu Qian | 13/11/2015 | 13/11/2015 | Fixed | Top K UI | The alignment is off when the table results display overlaps the bar charts display, especially for multiple entries in a single rank | 1 | Low | Resolve Immediately | Shing Hei, Chu Qian
83 | Chu Qian | 13/11/2015 | 13/11/2015 | Fixed | Top K JSON | The error message output for invalid fields were not displayed in the correct order | 5 | Medium | Resolve Immediately | Shing Hei, Chu Qian
84 | Chu Qian | 13/11/2015 | 13/11/2015 | Fixed | Basic App Report UI | There is misalignment of chart display for Basic App Report (App Category, Breakdown) | 1 | Low | Resolve Immediately | Shing Hei, Chu Qian
85 | Chu Qian | 13/11/2015 | 13/11/2015 | Fixed | Location Delete JSON | Invalid date and timestamp was not shown if we input invalid data | 5 | Medium | Resolve Immediately | Shing Hei, Chu Qian
86 | Chu Qian | 13/11/2015 | 13/11/2015 | Fixed | Advanced Overuse Report | The output for both the UI and JSON were wrong | 5 | Medium | Resolve Immediately | Shing Hei, Chu Qian
87 | Amos | 14/11/2015 | 14/11/2015 | Fixed | Smartphone Usage Heatmap | UI Misalignment | 1 | High | Resolve Immediately | Amos, Remy
88 | Amos | 14/11/2015 | 14/11/2015 | Fixed | ErrorPage | Error page crashes | 10 | High | Resolve Immediately | Amos, Remy
89 | Amos | 14/11/2015 | 14/11/2015 | Fixed | Smartphone Usage Heatmap | JSON output validation incorrect for date and time. | 5 | High | Resolve Immediately | Amos, Remy
90 | Amos | 14/11/2015 | 14/11/2015 | Fixed | Smartphone Usage Heatmap | JSON output incorrect | 5 | High | Resolve Immediately | Amos, Remy